## Checklist
Gait Pattern Recognition with an Arduino Nano 33 BLE Sense
Name, Vorname | Abishek Senthilkumar |  |  | cc: Contact person in company: | N/A
Matr.-Nr | 7025714 |  |  | Project partner: | N/A
|  |  |  | First examiner: | Prof. Dr. Elmar Wings
Name, Vorname | Bruna Teixeria
Matr.-Nr | 7026005
Name, Vorname | Fedor Kotiaev
Matr.-Nr | 7026007
Checklist
update every day!
No. | Topic | done | date
First two weeks
1 | read ProjectManagement/BestPractice.pdf | 1st Week | 2024-04-10
2 | fulfill author.xlsx |  | 2024-04-11
3 | Install TeXLive |  | 2024-04-10
4 | install TeXStudio |  | 2024-04-10
5 | install Sumatrapdf |  | 2024-04-10
6 | configure TeXStudio |  | 2024-04-10
7 | test template report |  | 2024-10-07
8 | test template poster |  | 2024-04-10
9 | test template Presentations/template |  | 2024-04-10
10 | install doxygen |  | 2024-04-10
11 | readme.md |  | 2024-04-10
12 | literature research | 2nd week | 2024-10-14
13 | bib file |  | 2024-10-14
14 | . |  | 2024-10-17
15 | pdf files |  | 2024-10-17
16 | presentation "Literature" |  | 2024-10-17
17 | challenges with citations |  | 2024-10-17
18 | write n introduction with citations |  | 2024-10-17
19 | presentation "Introduction" |  | 2024-10-17
20 | project plan | 3rd week | 2024-10-25
21 | fulfill the list "Resulting Objects" |  | 2024-10-25
22 | presentation "Project Plan" |  | 2024-10-25
23 | Readme.md |  | 2024-10-25
Processing the project
24 | update project plan | 4th week | 2024-11-07
25 | update the list "Resulting Objects" |  | 2024-11-07
26 | presentation "Project Plan" II |  | 2024-11-07
27 | rename all tex files along the project plan |  | 2024-11-07
28 | delete or add additional TeX or Python projects, e.g. Manual |  | 2024-11-07
29 | List of Material |  | 2024-11-07
30 | Manual |  | 2024-11-07
31 | domain knowledge | 5th week | 2024-11-13
32 | algorithm |  | 2024-11-13
33 | tools |  | 2024-11-13
34 | methodology |  | 2024-11-13
35 | database | 6th week | 2024-11-20
36 | database description |  | 2024-11-20
37 | database discussion |  | 2024-11-20
38 | Homework "Literature" | 7th week | 2024-11-28
39 | Homework "John Ousterhout" |  | 2024-11-28
40 | updated README.md |  | 2024-11-28
41 | updated Project plan | 8th weeek | 2024-12-07
42 | updated Resulting objects |  | 2024-12-07
43 | Evaluation |  | 2024-12-07
44 | Validation |  | 2024-12-07
45 | Homework "UpdatedLiterature" | 9th week | 2024-12-16
46 | Development structure |  | 2024-12-16
47 | Development Environment |  | 2024-12-16
48 | From Development to Deployment | 10 th weeek | 2024-12-25
49 | Flow Chart |  | 2024-12-25
50 | tests |  | 2024-12-25
Final stage
51 | check: all website as pdf-file? |  | 2025-01-07
52 | check: all pdfs in the folder Documents? |  | 2025-01-07
53 | check: all images okay? |  | 2025-01-07
54 | check spelling |  | 2025-01-10
55 | check: poster? |  | 2025-01-10
56 | print poster |  | 2025-01-10
57 | check: GitHub project |  | 2025-01-16
58 | ready minimal one day before deadline |  | 2025-01-10
59
60
61
62

## Project Plan V1.0 (eng.)
Gait Pattern with an Arduino Nano 33 BLE Sense
|  | Week of Year | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
|  | Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
SP No. | SP's Title | Duration
1 | Informative activities / literature | 2.5
2 | Writing the Readme | lifetime of project
3 | Monitoring the MyLiterature.bib | lifetime of project
4 | Writing the Literature Review | 1.5
5 | Writing the Introduction | 1.5
6 | Writing the Domain Knowledge (problem and Data) | 1.5
7 | Writing the List of Materials | 1.5
8 | Writing the Hardware Description | 1.5
9 | Writing the Software Description | 1.5
10 | Writing the Data Mining | 2
11 | Given documentation, Improvements, Translation | 2
12 | methodology | 0.5
13 | KDD process | 1.5
14 | Writing the Deployment | 1
15 | Code developmentDocumentation of the code | 6
16 | Submission of the report | 0
17 | Writing the Data description | 1
18 | Writing the Software BoM, requirements.txt and List of Packages, Tools,… | 1
19 | Program Flowchart | 1
20 | an important used Package - description | 1
21 | an important used Package - description | 1
22 | Hardware improvements | 1
23 | Writing the Tests (cade and report) - software | 1
24 | Writing the Tests - Hardware | 1
25 | Documentation developer | 1
26 | Addition to Documentation (Improvement, todo…) | 1
27 | Development Environment | 1
28 | Creating the Poster | 1
29 | Writing the Manual v.2 | 1
30 | Final review of the project | 1
31 | End of the project | 0
Vacation / holidays
Enrolement / Submission
Meetings
x = f(course of study)
Bruna Teixeria
Matr.-Nr. 7026005
1. Sem MBIDA
Project Plan for Machine Learning and Project T
cc: - Contact person in company: N/A
- Project partner: N/A
- First examiner: Prof. Dr. Elmar Wings
Abishek Senthilkumar
Matr.-Nr. 7025714
2. Sem MBIDA
Fedor Kotiaev
Matr.-Nr. 7026007
1. Sem MBIDA
project
report
Submission of the report

## Resulting objects
Gait Pattern Recognition with an Arduino Nano 33 BLE Sense
Name, Vorname | Abishek Senthilkumar |  |  | cc: Contact person in company: | N/A
Matr.-Nr | 7025714 |  |  | Project partner: | N/A
|  |  |  | First examiner: | Prof. Dr. Elmar Wings
Name, Vorname | Bruna Teixeria
Matr.-Nr | 7026005
Name, Vorname | Fedor Kotiaev
Matr.-Nr | 7026007
List of all Resulting Objects
Subtask | Resulting objects | done | date
Literature | List of keywords | done | Oct 10, 2024
| Brief description of the sources | done | Oct 15, 2024
| bib file | done | Oct 26, 2024
| Bibliography in the report | done | Oct 26, 2024
| pdf documents | done | Nov 25, 2024
| quality check | done | Jan 12,2024
| … | done
Problem Description | Done in the final report ".\report" on the section "1 Introduction" | done | Nov 8, 2024
Challenges | Done in the final report ".\report" on the section "1 Introduction" | done | Nov 8, 2024
Solution | Done in the final report ".\report" on the section "1 Introduction" | done | Nov 8, 2024
Data Type | Done in the final report ".\report" on the section "2 Domain" | done | Nov 25, 2024
Data acquisition | Done in the final report ".\report" on the section "2 Domain" | done | Nov 25, 2024
Data Quality and Quantity | Done in the final report ".\report" on the section "2 Domain" | done | Nov 25, 2024
Algorithms | Done in the final report ".\report" on the section "5. Data Mining: Convolutional Neural" | done | Nov 26, 2024
Hyperparameters | Done in the final report ".\report" on the section "5.5. Hyperparameters" | done | Nov 26, 2024
Requirements | Done in the final report ".\report" on the section "5.6. Requirements" | done | Nov 26, 2024
KDD process | Done in the final report ".\report" on the section "8. Knowledge Discovery in Databases (KDD) Process" | done | Dec 9, 2024
ML Pipeline | Done in the final report ".\report" on the section 15.4". KDD: Development" |  | Dec 9, 2024
Data Selection | Done in the final report ".\report" on the section "9. KDD: Development" | done | Dec 9, 2024
Data Preprocessing | Done in the final report ".\report" on the section15.4.2-15.4.4 ". KDD: Development" | done | Dec 9, 2024
Data transformation | Done in the final report ".\report" on the section "10.1 . KDD: Development" | done | Dec 9, 2024
Data mining | Done in the final report ".\report" on the section "10.2 &15.4.5. KDD: Development" | done | Dec 9, 2024
Evaluation | Done in the final report ".\report" on the section "15.4.6. Evaluation and Verification" | done | Dec 11, 2024
Validation | Done in the final report ".\report" on the section "15.4.6. Evaluation and Verification" | done | Dec 11, 2024
Deployment | Done in the final report ".\report" on the section "11. Evaluation and Verification" | done | Dec 11, 2024
Data Descritption | Done in the final report ".\report" on the section 9 | done | Dec 11, 2024
Software BOM & requirements.txt | Done in the final report ".\report" on the sectiion 12.2 &12.3 | done | Jan 8, 2025
Development environment | Done in the final report ".\report" on section 13 | done | Jan 8, 2025
Programme Flow Chart | Done in the final report ".\report" on section 14 | done | Jan 8, 2025
project code and doxygen Documentation | Don in "Code\GaitPatternRecognition | done | Jan 8, 2025
Documentation Development (tech doc) | Done in the final report ".\report" on section 15 | done | Jan 11, 2025
Software Tests | Done in the final report ".\report" on section 16 and Code/GaitPatternRecognition | done | Jan 11, 2025
Poster | Done in the final report ".\report" done in ".\poster | done | Jan 16, 2025
TensorFlow package description | Done in the final report ".\report" on section 6 | done | Jan 16, 2025
Hardware Tests | Done in the final report ".\report" on section 3.4 | done | Jan 21, 2025
Numpy package description | Done in the final report ".\report" on section 7 | done | Jan 21, 2025
Manual Completion | Done in the manual | done | Jan 21, 2025
Results | Done in the final report ".\report" on section 17 | done | Jan 21, 2025
Conclusions | Done in the final report ".\report" on section 18 | done | Jan 21, 2025
Future Work | Done in the final report ".\report" on section 18.2 | done | Jan 28, 2025
Projectplan-Project (10credits) in Master Course "Business Intelligence and Data Analytics"